## RTM
BR ID | Business requirement | FR ID | User Story | UAT | Evidence | Acceptance criterion | Priority | Status
BR-01 | Core KPI baseline | FR-01 | US-001 | UAT-001 | E-001,E-002 | Core KPI totals reconcile to source aggregation | High | Open
BR-02 | Dimension analysis | FR-02 | US-002 | UAT-002 | E-003,E-006,E-007,E-008 | Region/product/segment/channel results reconcile to source grouping | High | Open
BR-03 | Aligned-period comparison | FR-03 | US-003 | UAT-003 | E-002,E-003 | Q3→Q4 absolute and percentage movement matches source aggregation | High | Open
BR-04 | Business focus identification | FR-04 | US-004 | UAT-004 | E-010 | Focus is labelled as business context, not falsely as largest decline | High | Open
BR-05 | Service signal analysis | FR-05 | US-005 | UAT-005 | E-004,E-005 | SLA and tickets/order use the same comparison period | High | Open
BR-06 | Cancellation evidence sufficiency | FR-06 | US-006 | UAT-006 | E-009,E-010 | Insufficient cancellation volume blocks causal interpretation | High | Open
BR-07 | Evidence classification | FR-07 | US-007 | UAT-007 | E-009,E-010 | Material findings are labelled evidence, hypothesis or gap | High | Open
BR-08 | Evidence traceability | FR-08 | US-008 | UAT-008 | E-001–E-010 | Export retains evidence IDs | High | Open
BR-09 | Validation-aware recommendations | FR-09 | US-009 | UAT-009 | E-009,E-010 | Recommendation includes action, owner status, measure and dependency | High | Open
BR-10 | Management-ready exports | FR-10 | US-010 | UAT-010 | E-001–E-010 | Exports are readable and internally consistent | Medium | Open